## Bugs
Id | LoggedBy | Status | Date | Type | Severity | Priority | DAXX | Time | Url | Description (Steps to reproduce) | Error message | Required changes | Files | FixedBy | FixDate | FixRelease | Comments Daxx | Comments MARPA
1 | WSTEE | NEW | 2011-09-27 | 1 | 100 | P1 | Bug | 2 | http://localhost:8020/admin/Users/Default.aspx | - Go to admin - Click on "Manage users" | Errormessage: The control with ID 'updatePanel' requires a ScriptManager on the page. The ScriptManager must appear before any controls that need it.
2 | WSTEE | NEW | 2011-09-28 | 0 | 30 | P3 | Bug | 2 | http://localhost:8020/Wizard/Step1.aspx | - Go to admin - Click on "New item type creation " - Type in the textbox "Description" - Use "Ctrl Left Arrow" or Ctrl Right Arrow" to navigate between the words Ctrl Arrow Left/Right has the same functionality as Alt Arrow Left/Right, meaning the browser is navigating to the previous/next page? |  | Remove the Ctrl-Left/Right/… behaviour in the page
3 | WSTEE | NEW | 2011-09-28 | 0 | 30 | P3 | Not possbile to reproduce |  | http://localhost:8020/Wizard/Step3.aspx | Same as bug ID 2, but then using the Home button …!? Strange behaviour, also saving the attribute 4 or 5 times when pressing the Home button?
4 | WSTEE | NEW | 2011-09-28 | 6 | 30 | P4 | Not a bug |  |  | 4.1.4.4 Choosing Screen view in functional design document isn't implemented | Pagina 16 ontwerp | Add functionality, see functional design |  |  |  |  | Remarks: It is developed, but it is not available in this way. The screens are seperated, because it is not possible to do actions with a screen if an asset is not created. So after creating an asset, go to editting of the assets, from there you can manage the screens for the asset. | This item is about 4.1.4.4, the two extra screen layouts possibilities, with a full width block at the bottom. It's a pity the screens can't be configured on one place, but OK for that …
5 | WSTEE | NEW | 2011-09-29 | 1 | 100 | P1 | Bug | 4 | http://localhost:8020/Wizard/Step7.aspx http://localhost:8020/Wizard/Step11.aspx | First time: Created an extra panel for a screen. When clicking next to pick fields for the different panels, I got the error Second time: I removed the extra panel, only "General" left over. Continued configuring just bij clicking next. Finally, clicked save to save the asset, and got again the error message. | An object with the same key already exists in the ObjectStateManager. The ObjectStateManager cannot track multiple objects with the same key.
6 | WSTEE | NEW | 2011-10-03 | 6 | 30 | P4 | Bug | 4 | http://localhost:8020/admin/AdditionalScreens/AdditionalScreenStep4.aspx | Steps to follow: - Item Type Editing - Click on screens icon - Create new screen - Choose column layout - Create new panel There is no functionality to create multi language extra screens |  | Add multilanguage functionality to screens, but also tasks, … | Images/BUG_ID0006.jpg
7 | WSTEE | NEW | 2011-10-03 | 2 | 30 | P3 | Bug | 4 | http://localhost:8020/admin/AdditionalScreens/AdditionalScreenStep5.aspx | Steps to follow: - Item Type Editing - Click on screens icon - Create new screen - Choose column layout - Create some new panels - Select some fields (not all) from the assets to the panels - Try to finish The "Finish" button can't be clicked? Maybe because some necessary fields aren't selected? But then, there has to be an error-message |  | Create visual UI messages that help the user configuring the panels and give good feedback when clicking on Finished and something is wrong | Images/BUG_ID0007.jpg
8 | WSTEE | NEW | 2011-10-03 | 2 | 20 | P5 | RFC | 16 | http://localhost:8020/admin/AdditionalScreens/AdditionalScreenStep2.aspx?ScreenId=12 | Use the same UI design in the left column when creating/configuring extra screens/panels as the "basic" configuration (see image) |  |  | Images/BUG_ID0008.jpg |  |  |  |  | Was this asked to use a different layout for the left column?
9 | WSTEE | NEW | 2011-10-03 | 2 | 20 | P5 | Bug | 3 | http://localhost:8020/admin/AdditionalScreens/AdditionalScreenStep2.aspx?ScreenId=12 | No breadcrumb when defining extra screens/panels |  | Configure breadcrumb in the whole application. There are too many places where it's wrong or where isn't a breadcrumb at all
10 | WSTEE | NEW | 2011-10-03 | 2 | 20 | P5 | Bug | 3 |  | In the admin module, the breadcrumb must aways start with Home > Admin > … so you can always go back to the admin main page by clicking on "Admin". Now, when for example using the wizard, the breadcrumb is Home > Wizard > …
11 | WSTEE | NEW | 2011-10-03 | 2 | 20 | P5 | RFC | See 8 | http://localhost:8020/admin/Tasks/TasksList.aspx?AssetTypeId=100 | Use the same UI design in the left column when creating/configuring extra screens/panels as the "basic" configuration (see bug ID 8) | [7 empty] | Was this asked to use a different layout for the left column?
12 | WSTEE | NEW | 2011-10-03 | 1 | 50 | P1 | Bug | 2 | http://localhost:8020/admin/Tasks/Default.aspx | I created a new task with these properties: - Function Type: Create Item - Select Screen: BUB Dossier (created extra screen with multi panels) When I go to tasks and click on this task I get a popup message saying: "Task is being executed". Then a refresh of the screen occurs, that's all. |  | The popup message has to disappear and most important, a screen to create a new item based on the selected screen must be shown
13 | WSTEE | NEW | 2011-10-03 | 6 | 30 | P4 | Bug | 4 | http://localhost:8020/admin/Tasks/EditTask.aspx?AssetTypeId=100&TaskId=3&Edit=1 | There is no multilanguage functionality when creating tasks. Tasks also must be configured in multiple languages (EN, NL, FR). See screens in § 4.2 from the Functional Design
14 | WSTEE | NEW | 2011-10-03 | 2 | 20 | P5 | RFC | 16 | http://127.0.0.1:8080/admin/ZipsAndPlaces.aspx | UI for adding places and zipcodes is not "smart". You need a lot of mouse clicks to add places and link them … In Belgium, there is often the same zipcode for different places. So one of the extensions must be the possibility to select more then one place. | Gewoon hetzelfde als in assetmanager | I would make it just one table with zipcode + place?
15 | WSTEE | NEW | 2011-10-03 | 1 | 30 | P4 | RFC | 0 | http://localhost:8020/admin/Tasks/EditTask.aspx?AssetTypeId=100&TaskId=6&Edit=1 | Steps to follow: - Go to admin - Item type editing - Click on Tasks from an asset - Create a new task - Pick "Save Search" from the list - Fill in some keywords in the search input form - Click on Finished Because the search is not executed (by pressing the search button), another search config (previous executed?) will be saved. Because the SEARCH button is on the right and difficult to see, you will miss it and think you have to press the FINISHED button. |  | Change the Look & Feel of the Search form, like designed for the Asset Management System (see image) - Button below and centered, grey color In the Functional Design, launching the search form in a new window/tab is proposed so it is clear that the user has to configure the search. So this approach is preferred. Give feedback to the user using messages. Check if there is anything to save. If the search isn't proper configured, give a message to the user. Create a textbox where the user can see the search configuration (xml, ...?). This makes it clear that something is configured and will be saved (see screenshots in Function Design! - § 4.2.3) | BUG_ID0015.jpg |  |  |  |  | This is not really a RFC because the behaviour and the screen shots are designed as requested in this item. Make it in any case more transparant … In a future version (HRM Asset Management), this option must be made as requested at no cost.
16 | WSTEE | NEW | 2011-10-03 | 1 | 30 | P4 | Not possbile to reproduce |  | http://localhost:8020/admin/Tasks/EditTask.aspx?AssetTypeId=100&TaskId=6&Edit=1 | Steps to follow: - Go to admin - Item type editing - Click on Tasks from an asset - Create a new task - Pick "Save Search" from the list - Click on the tab "By Context" - Create a new search row - Press the button "Finished" A popup is displayed with the message: "Session expired. Please reload the page". | Ik heb hem drie keer op rij | Same arguments as previous bug (ID 15). |  |  |  |  | Not related to bug id 15
17 | WSTEE | NEW | 2011-10-04 | 6 | 50 | P3 | Not a bug |  | http://127.0.0.1:8080/admin/Tasks/EditTask.aspx?AssetTypeId=3 | When creating a new task of the type "Export file", there are no options to configure the export task. | Wat is dan standaard export? | Read § 4.2.2 and § 4.2.3.4. Export configuration options must be possible by configuring a SSIS or external EXE program (with/without parameters), but export has also be possible by configuring the selection by defining a resultset. So, the same as for the task Function typ "Save Search", but when executing, the results must be exported to an Excel file and offered as a download link |  |  |  |  | An export, based on an SSIS package must be done through the option "Launch batch task". From here the SSIS options are available. Standard exports are availble through the "Export file".
18 | WSTEE | NEW | 2011-10-04 | 6 | 50 | P2 | Bug | 4 | http://localhost:8020/admin/Tasks/EditTask.aspx?AssetTypeId=100 | The task Function Type "Print Report" is missing. |  | Please read § 4.2.2 and § 4.2.3 in the functional design document. It is important that an asset (for ex. a concrete BUBDossier) can be linked to a report. In the detail form (see document + included image), it has to be possible to launch a report that prints the current BUBDossier (asset). If questions, please contact us!
19 | WSTEE | NEW | 2011-10-04 | 1 | 100 | P1 | Bug | 6 | http://localhost:8020/admin/Taxonomies/TreeEdit.aspx?Uid=77&Edit=1 | Steps to follow: - Goto create/edit taxonomies - Choose edit for the default taxonomy (categories) - Add a new root node - Add a new sub node to the newly created root node - Press Save and/or Publish | Cannot insert duplicate key row in object 'dbo.TaxonomyItem' with unique index 'TaxonomyItemIdTaxonomyRevision'. The statement has been terminated. See for more info the file Errors\Error_ID19.htm
20 | WSTEE | NEW | 2011-10-04 | 1 | 50 | P1 | Bug | 4 | http://localhost:8020/admin/Taxonomies/TreeEdit.aspx?Uid=77&Edit=1 | It is not possible to change the text of existing taxonomy items. This must be possible!
21 | WSTEE | NEW | 2011-10-04 | 1 | 100 | P1 | Bug | 4 | http://localhost:8020/Wizard/Step11.aspx | Similar to bug with ID 5. It is impossible to create/change assets in the admin (item type editing). See error for more information Steps to follow in the tested scenario: - Goto admin - Goto item type editing - Pick BUBDossier - Create a new (required) attribute - Add the attribute to a panel - Click next next ... until the last page - Click Save and/or Publish See error for more information | An object with the same key already exists in the ObjectStateManager. The ObjectStateManager cannot track multiple objects with the same key. See errorpage (Errors\Error_ID21.htm for more info)
22 | WSTEE | NEW | 2011-10-04 | 1 | 100 | P1 | Bug | 4 | http://localhost:8020/Wizard/Step11.aspx | Steps to follow: - Go to admin - Goto item type editing - Pick BUBPerson assettype - Change the Gender datatype from bool to char - Save and/or publish See error for more info | The INSERT statement conflicted with the FOREIGN KEY constraint "FK_AttributePanel_ScreenId". The conflict occurred in database "sobenbub", table "dbo.AssetTypeScreen", column 'ScreenId'. See Errors\Error_ID22.htm file for the complete error message page
23 | WSTEE | NEW | 2011-10-04 | 1 | 100 | P1 | Bug | 4 | http://localhost:8020/Asset/View.aspx?AssetUID=0&AssetTypeUID=110 | For BUBDossier are two different screens configured, one is the default and one is with links to other asset types (because default not possible yet) Steps to follow - Create new BUBDossier - Switch to alternative layout - Switch back to default layout See errormessage for more info | Object reference not set to an instance of an object. See Errors\Error_ID23.htm for the complete error message page
24 | 24 | 24 | 2011-10-04 | 1 | 100 | P1 | Not relevant |  |  | Errorhandling must be done different. It's OK for test purposes, but an enduser isn't supposed to see a "hard" error message. So "possible" errors must be better coded. All unexpected errors (like DB fail, network fail, …) can be handled by writing a module for (custom) exception handling. | [7 empty] | I think it is relevant, because there is at the moment no proper error handling and all unhandled errors (all of them?) are shown to the end user.
25 | WSTEE | NEW | 2011-10-04 | 1 | 100 | P1 | Bug | 4 | http://localhost:8020/Asset/Edit.aspx?AssetUID=1&AssetTypeUID=110&ScreenId=12&LayoutId=1 | Steps to follow - Create a new BUBDossier with the defaultscreen, so only the basic BUBDossier is created without many links to other assets (null) - Edit the BUBDossier and switch to the alternative screen layout with links to more assets. See error for more information | Cannot obtain related asset. See Errors\Error_ID25.htm for the complete error description | Errors must be handled better. However, it has to be possible to create a basic asset with a default screen without links to other assets. By editing the asset, it has to be possible to switch to another screen so additional information (linked assets) can be added. So for example, a BUBDossier can be created without a link to the previous company. After some time, the BUBDossier is edited by using a different screen where the previous company/companies can be added. This must be done without an errormessage and with the already provided information filled in and the other fields blank, ready to be filled in.
26 | WSTEE | NEW | 2011-10-04 | 1 | 80 | P2 | Bug | 4 |  | Steps to follow: - For BUBDossier, create an additional extra screen - Create a new BUBDossier (don't know if it's necessary) - Alter the BUBDossier (activitated the auto generate name option) - Check the extra screens, they are all gone |  | When a new revision is created, screens and tasks must be copied and linked to the newly created DynEntityConfigUid.
27 |  |  | 2011-10-04 | [5 empty] | FO | See Page 12 and 13 FO | Multilanguage
28 |  |  | 2011-10-04 | [5 empty] | FO | See page 13 | Default web form
29 |  |  | 2011-10-04 | [5 empty] | FO | See File Export Page 17 | File export
30 |  |  | 2011-10-04 | [5 empty] | FO | See Page 18 | SortPriority
31 |  |  | 2011-10-04 | [5 empty] | FO | See Page 21 and 22 | SSIS Packages
32 |  |  | 2011-10-04 | [5 empty] | FO | Page 22 | Export to an excel (and/or xml file) based on a preconfigured resultset (search)
33 |  |  | 2011-10-04 | [5 empty] | FO | Page 23 | link can be created between the report and the asset
34 |  |  | 2011-10-04 | [5 empty] | FO | Page 24 | SortPriority field to tasks
35 |  |  | 2011-10-04 | [5 empty] | FO | Page 25 | Some UI adaptions

## Codes
Types of Severity:
100 | Blocker: No further testing work can be done.
80 | Critical: Application crash, Loss of data.
50 | Major: Major loss of function.
30 | Minor: minor loss of function.
20 | Trivial: Some UI enhancements.
10 | Enhancement: Request for new feature or some enhancement in existing one.
The report types are typically:
1 | Coding error
2 | Design error
3 | New suggestion
4 | Documentation issue
5 | Hardware problem
6 | Missing
Priority
P1 | Fix the bug with highest priority
P5 | Fix when time permits

## Test list
Id | Description
1 | Integration SSIS and external exe programs, with the use of parameters